## Gantt Chart
Resume Screening AI SaaS Platform — Gantt Chart
Project Start: March 02, 2026 ¦ Project End: April 13, 2026 ¦ Total Duration: 42 days
[6 empty] | March 2026 |  |  |  |  | April 2026
Phase | Task | Owner | Start Date | End Date | Days | Mar 02 | Mar 09 | Mar 16 | Mar 23 | Mar 30 | Apr 06 | Apr 13
1. Initiation
| Project Charter & SaaS Requirements | PM | Mar 02 | Mar 05 | 3
| Vendor Selection & Account Setup | Tech Lead | Mar 02 | Mar 04 | 2
| Development Environment & Repo Setup | DevOps | Mar 02 | Mar 04 | 2
2. Architecture
| Database Schema Design (ERD) | Architect | Mar 05 | Mar 10 | 5
| UI/UX Wireframing | Designer | Mar 05 | Mar 12 | 7
| Security Architecture | Security Lead | Mar 05 | Mar 08 | 3
3. Backend Dev
| FastAPI Boilerplate & Auth Middleware | Backend Dev | Mar 12 | Mar 17 | 5
| AI Logic Migration & Optimization | AI Eng | Mar 12 | Mar 22 | 10
| Core APIs (Resume Uploads, Job Posts) | Backend Dev | Mar 12 | Mar 22 | 10
| Subscription Logic & Intasend Integration | Backend Dev | Mar 12 | Mar 19 | 7
| Email Notification System | Backend Dev | Mar 12 | Mar 15 | 3
4. Frontend Dev
| React Project Structure & UI Library | Frontend Dev | Mar 22 | Mar 27 | 5
| Candidate Portal | Frontend Dev | Mar 22 | Mar 30 | 8
| HR Dashboard & Analytics | Frontend Dev | Mar 22 | Apr 03 | 12
5. QA
| Integration Testing | QA | Apr 03 | Apr 10 | 7
| User Acceptance Testing | PM | Apr 03 | Apr 08 | 5
6. Deployment
| Production Deploy & Go-Live | DevOps | Apr 10 | Apr 13 | 3
Phase Legend:
1. Initiation
2. Architecture
3. Backend Dev
4. Frontend Dev
5. QA
6. Deployment