## Gantt & Tasks
ID | Phase | Task | Start | Duration | Owner | Predecessors | End Date | % Complete | Status
1.1 | 1. Initiation | Project Charter & SaaS Requirements Definition | 2026-02-12 | 3 | PM | - | 2026-02-15 | 25 | In Progress
1.2 | 1. Initiation | Vendor Selection & Account Setup (Clerk, Supabase, Intasend) | 2026-02-15 | 2 | Tech Lead | 1.1 | 2026-02-17 | 0 | Pending
1.3 | 1. Initiation | Development Environment & Repo Setup | 2026-02-17 | 2 | DevOps | 1.2 | 2026-02-19 | 0 | Pending
2.1 | 2. Architecture | Database Schema Design (ERD) & SaaS Data Model | 2026-02-19 | 5 | Architect | 1.3 | 2026-02-24 | 0 | Pending
2.2 | 2. Architecture | UI/UX Wireframing (HR Dashboard & Candidate Portal) | 2026-02-24 | 7 | Designer | 2.1 | 2026-03-03 | 0 | Pending
2.3 | 2. Architecture | Security Architecture (RLS, Auth Policies) | 2026-03-03 | 3 | Security Lead | 2.1 | 2026-03-06 | 0 | Pending
3.1 | 3. Backend Dev | FastAPI Boilerplate & Auth Middleware (Clerk) | 2026-03-06 | 5 | Backend Dev | 2.3 | 2026-03-11 | 0 | Pending
3.2 | 3. Backend Dev | AI Logic Migration (NLP/Matching Engine) & Optimization | 2026-03-11 | 10 | AI Eng | 3.1 | 2026-03-21 | 0 | Pending
3.3 | 3. Backend Dev | Core APIs (Resume Uploads, Job Posts, Matching) | 2026-03-21 | 10 | Backend Dev | 3.2 | 2026-03-31 | 0 | Pending
3.4 | 3. Backend Dev | Subscription Logic & Intasend Payment Integration | 2026-03-31 | 7 | Backend Dev | 3.3 | 2026-04-07 | 0 | Pending
3.5 | 3. Backend Dev | Email Notification System (Resend) | 2026-04-07 | 3 | Backend Dev | 3.4 | 2026-04-10 | 0 | Pending
4.1 | 4. Frontend Dev | React Project Structure & UI Component Library | 2026-04-10 | 5 | Frontend Dev | 2.2 | 2026-04-15 | 0 | Pending
4.2 | 4. Frontend Dev | Candidate Portal (Job View, Upload, Apply) | 2026-04-15 | 8 | Frontend Dev | 4.1 | 2026-04-23 | 0 | Pending
4.3 | 4. Frontend Dev | HR Dashboard (Analytics, Matches, Billing) | 2026-04-23 | 12 | Frontend Dev | 4.2 | 2026-05-05 | 0 | Pending
5.1 | 5. QA | Integration Testing (Payments, End-to-End) | 2026-05-05 | 7 | QA | 4.3 | 2026-05-12 | 0 | Pending
5.2 | 5. QA | User Acceptance Testing (Beta) | 2026-05-12 | 5 | PM | 5.1 | 2026-05-17 | 0 | Pending
6.1 | 6. Deployment | Production Deploy (Render) & Go-Live | 2026-05-17 | 3 | DevOps | 5.2 | 2026-05-20 | 0 | Pending

## Risk Register
Sort | Risk Description | Impact | Prob | Mitigation
1 | Integration failure with Intasend | High | Med | Early proofs of concept; Sandbox testing
2 | AI Accuracy below expectations | High | Med | Manual review feature for HR; Model fine-tuning
3 | Free tier resource exhaustion | Med | High | Budget allocated for paid tiers ( buffer)
4 | Timeline Delays | Med | Med | Buffer days added to critical path

## Resources
Name | Role | Rate/Hr | Allocation
Project Manager | Administrator | 50 | 20%
Backend Dev | Developer | 40 | 100%
Frontend Dev | Developer | 40 | 100%
QA Engineer | Tester | 30 | 50%

## Budget
Item | Type | Monthly Cost | Qty | Total
Render Hosting | Opex | 7 | 12 | 84
Supabase Pro | Opex | 25 | 12 | 300
Domain Name | Capex | 15 | 1 | 15
Dev Tools | Capex | 0 | 1 | 0
Marketing/Ads | Opex | 100 | 3 | 300