## Executive Summary
Section | Details
Project Title | Resume Screening AI SaaS Platform
Project Manager | Administrator
Start Date | 2026-02-12
End Date | 2026-06-05
Budget Estimate | -500 (free tiers initially)
Success Criteria | 95% uptime, 90% AI accuracy, 100 users in 6 months

## Project Scope
Type | Item
In Scope | Backend: FastAPI with AI logic
In Scope | Frontend: React/TS HR dashboard & candidate portal
In Scope | Database: Supabase with RLS
In Scope | Auth: Clerk for HR
In Scope | Payments: Intasend subscriptions
In Scope | Emails: Resend confirmations
In Scope | Hosting: Render
Out of Scope | Mobile apps
Out of Scope | Advanced AI models (e.g., BERT)
Out of Scope | Non-subscription features
Assumptions | Workspace code migratable
Assumptions | Free tiers suffice initially
Constraints | Python-based AI
Constraints | No vendor lock-in

## Objectives and Goals
Category | Goal
Business Goals | Monetize AI via subscriptions
Business Goals | Target HR in Africa/global
Technical Goals | Secure, scalable architecture
Technical Goals | <500ms DB queries
Functional Goals | HR dashboard with analytics
Functional Goals | Candidate upload interface
Functional Goals | Email confirmations
Quality Goals | 90%+ AI accuracy
Quality Goals | GDPR compliance

## Stakeholders
Role | Name | Responsibility
Project Manager | Administrator | Overall timeline, budget, scope
Tech Lead / Dev | Developer | Architecture, API implementation
QA / Tester | TBD | Testing functionalities

## Project Timeline
Phase | Task | Start | End | Duration(Days) | Owner
1. Initiation | Project Charter & SaaS Requirements |  |  | 3 | PM
1. Initiation | Vendor Selection & Account Setup |  |  | 2 | Tech Lead
1. Initiation | Development Environment & Repo Setup |  |  | 2 | DevOps
2. Architecture | Database Schema Design (ERD) |  |  | 5 | Architect
2. Architecture | UI/UX Wireframing |  |  | 7 | Designer
2. Architecture | Security Architecture |  |  | 3 | Security Lead
3. Backend Dev | FastAPI Boilerplate & Auth Middleware |  |  | 5 | Backend Dev
3. Backend Dev | AI Logic Migration & Optimization |  |  | 10 | AI Eng
3. Backend Dev | Core APIs (Resume Uploads, Job Posts) |  |  | 10 | Backend Dev
3. Backend Dev | Subscription Logic & Intasend Integration |  |  | 7 | Backend Dev
3. Backend Dev | Email Notification System |  |  | 3 | Backend Dev
4. Frontend Dev | React Project Structure & UI Library |  |  | 5 | Frontend Dev
4. Frontend Dev | Candidate Portal |  |  | 8 | Frontend Dev
4. Frontend Dev | HR Dashboard & Analytics |  |  | 12 | Frontend Dev
5. QA | Integration Testing |  |  | 7 | QA
5. QA | User Acceptance Testing |  |  | 5 | PM
6. Deployment | Production Deploy & Go-Live |  |  | 3 | DevOps

## Budget and Resources
Category | Item | Cost Type | Estimated Cost (USD) | Notes
Hosting | Render | Monthly | 20 | Free initially
Database | Supabase Pro | Monthly | 25 | Only if DB 500MB exceeded
Auth | Clerk | Monthly | 25 | Free up to 10k users
Emails | Resend | Monthly | 20 | Free tier sufficient
Payment | Intasend Fees | Per Txn | 0 | Takes percentage cut
Misc | Domain Name | Annual | 15 | One time purchase
105

## Risk Management
Risk ID | Description | Probability | Impact | Mitigation
R1 | Intasend Payment Failures | Medium | High | Robust error handling, Sandbox testing
R2 | AI Matching Accuracy Low | Medium | High | Manual review feature, Model fine-tuning
R3 | Supabase Free Tier Limits | High | Medium | Monitor usage, Budget for upgrade
R4 | Data Privacy (GDPR) | Low | Severe | Data encryption, Clear privacy policy

## Quality Assurance
Testing Type | Description | Responsible | Standards
Unit Tests | NLP accuracy, API endpoints | Dev | PEP8, TypeScript linting
Integration Tests | End-to-End flows, Payments | QA | 95% coverage
UAT | Beta user feedback | PM | User feedback loop
Security Audit | RLS policies, GDPR compliance | Security Lead | OWASP guidelines

## Change Management
Process | Details
Document changes in GitHub | Review weekly
Approval for major changes | Impact on timeline/budget

## Communication Plan
Audience | Method | Frequency
Internal Team | Daily stand-ups, Weekly reports | Daily/Weekly
External Users | Feedback forms, Emails | As needed
Vendors | API docs, Support tickets | On-demand

## Procurement
Vendor | Purpose | Contract Type | Status
Render | Hosting | Free/Paid | Setup
Supabase | Database | Free/Paid | Setup
Clerk | Auth | Free | Setup
Intasend | Payments | Free/Paid | Setup
Resend | Emails | Free | Setup

## Closure and Handover
Criteria | Details
MVP deployed, 1 user onboarded | Final review by PM
Handover Items | Source code, API docs, User guides, Maintenance plan